## Slide 1: Oracle Apps Project Methodologies, Tool and Delivery Model

## Slide 2: What to Expect from the session
After the session there will be clear understanding of below mentioned topics
Project Lifecycle
Delivery Model
Key Roles &
Responsibilities etc

## Slide 3: Topics
Overall Project Approach
Data Migration
Post Go Live Support
Managing Development
Testing
ADM Service Model
Tools & Accelerators
Project Organization Structure
ADM Typical Delivery Organization

## Slide 4: Overall Project Approach – Global Template & Pilot followed by clusters
Global level activity
Activity per cluster
Cluster Design
Alignment / Conference Room Pilot
Configure, Build & Unit Test
DM Build & Unit Test
System Test & Regression Test
System Integration Test
End User Training
User Acceptance Test
Production Cutover
Project Initiation
Solution Definition
Solution Development
Implementation
Post Implementation
Support
Overall Implementation Plan
AS-IS Study
Requirements Gathering
Global Design Template Analysis & Design
Future State Solution Map
Strategy Definitions
Configure, Build and Unit Test
DM Build & Unit Test
Pilot CRP
System Test
Hand-over to IT / Support
Early Life Support
System Integration Test
User Acceptance Test
End User Training
Production Cutover
Early Life Support
Handover to IT / Support
Activity for pilot
Repeated Activities – each cluster

## Slide 5: Phase wise Key Activities
Align, Plan and Mobilize
  Kick off the project and onboard the project team
  Agree on project vision, objectives and scope
  Agree on project acceptance criteria
  Identify and Mobilize key stakeholders (Customer Project Team and representatives for Global Core design team from required countries)
Finalize the overall Implementation Plan
  Discuss and finalize the Cluster approach
  Finalize the Rollout strategy for the Clusters
  Refine the Project Plan (current work package)
Conduct AS-IS Study and Gather requirements
  Understand the current Customer processes, Business functions performed at each of countries in scope
  As-Is System walkthrough to understand critical business process and Strategic Customizations
  Conduct Inventory assessment of existing System documentation and test scripts
  Conduct requirement session to gather requirement for new modules
  Identify local requirements of each country having an impact on global design template (to the extent possible)
Analysis & Design
  Mapping Customer Processes to R12 process
  Perform Gap-Analysis and identify Gaps
  Propose Solutions for Gaps - Workarounds and Customizations
  Challenge customization & identify Standard functionality to replace customization
  Design new /changes in organization structure , key elements like CoA
Future Solution
  Document Future State Process Flows and Business Rules
  Document Application Configuration – BR100
  Finalize the technical Development Register – Customizations, Integrations and Data Migrations
Develop Strategy documents
  Develop Release Management, Data Migration, Testing, Training, Production Cutover Strategies
Conference Room Pilot (CRP)
  Validate the Global Design Template by conducting CRP for top 20 Business Scenarios for Pilot
  Identify top 5 Biz Scenarios per Process streams to be covered in CRP per Cluster
  Only Standard Oracle functionalities are covered in CRP for Pilot
  Freeze the scope of the solution
Project Initiation
Solution Definition

## Slide 6: Phase wise Key Activities
Configure, Build and Test
  Configure Application based on BR100 inputs
  Develop Functional Specifications for Technical Components
  Develop and Unit Test Technical Components
Data Migration Build & Test
  Develop Functional Specifications for Data Migration
  Develop Data Migration Routines and Unit Test
  Run Data Migration Iteration#1 – System Test (60% of Data)
System Test
  Create Test scripts for Testing - System Test
  Create Regression Test Scripts – Base Pack
  Create Performance Testing scenarios and Scripts
  Perform System Test by Capgemini covering critical business processes for 1 Legal Entity in Pilot Country
  Fix System Test Defects
System Integration Test
  Support Customer in executing System Integration Testing
  Fix System Integration Test Defects
Prepare for Implementation Phase
  Prepare Rollout Kit, develop Training Material & finalize Training Schedule
  Finalize the Cutover Plan
End User Training
  Conduct Trainings – Train-the-Trainer
Performance and User Acceptance Test
  Perform Performance Tests
  Prepare UAT Instance – Configure
  Run Data Migration Iteration#2 – UAT (90% of Data)
  Fix User Acceptance Test Defects
Production Cutover
  Run Data Migration Iteration#3 – Pre-Prod (100% of Data)
  Production Cutover activities
Solution Development
Implementation
Production Problem Resolution
  Provide resolutions to Production Problems
Handover to IT/Support Team
  Handover the system and project documentation to Support Team
Post Production Support

## Slide 7: Deliverables (Capgemini & Customer) and Milestones
Phases | Deliverable | Milestone
Initiation | Updated project plan Project Acceptance Criteria and Procedures Requirements Definition Updated Clusters and Rollout Plan Project Environment Plan – Instance Planning (if required) | Project Kick-Off Requirements Sign-Off
Solution Definition | To-Be Business Process Flows/ To-Be Solution Map / Global Solution Document Gap Register and / or Technical Development Register Application Configuration (BR100) Release Strategy Data Migration Strategy & Plan Testing strategy & Plan Training Strategy & Plan Production Migration / Cutover Strategy & Plan | Solution Design Sign-Off Release and Configuration documents
Solution Development | Functional design documents Technical design documents Technical Components – Code and Installation Scripts Training Material System test plan, scripts and results System Integration test plan, scripts and results (Customer) Production Cutover plan | Technical Development Complete System Test Complete System Integration Test Completion (Customer)
Implementation | UAT Test Results (Customer) | User Acceptance Test Sign-Off (Customer) Production Go-Live
Post-Production Support | Defect fixes | End of Support

## Slide 8: Managing Development
Core Solution Design | 
Solution Development | 
Implement | 
Post Production Support | 
Develop Functional Specifications
Review Functional Design Completeness & Open Items
Prepare Technical Design
Develop & Unit Test Customizations
Peer Review Technical Design & Code
With Technical Team
Accept - Design
Perform Functional Unit Test
Prepare Installation Script / Patch
Review Comments / Rework
Bugs / Rework
Reviewed and Tested Customization
Perform Pre-UAT
Pre-UAT Bug Fixing
Perform UAT
UAT Bug Fixing
Production Deployment
Post Prod and Warranty Support
1
Aligned to Coding Standards
Handover to AM
3
Customer
Capgemini
Gap-Analysis
Build Development Register
Impact Assessment of Existing Objects
Perform SIT
SIT Bug Fixing
2
1
Capgemini Technical Team Accept - Design
2
Capgemini Functional Team Approves - Development
3
Customer Accept - Development
Define Technical Architecture

## Slide 9: Data Migration Quality enhanced through multiple dress rehearsals
Capgemini Scope of data migrations is limited to:
  Master data
  Open transactions
  Custom Tables
Historical Data is not considered in scope.
Comprehensive Migration Strategy
Involve all relevant stakeholder
Data Cleansing and transformation requirements finalized in Solution Definition Phase
Use proprietary Data Migration Toolkit
Focus on Data Quality and Cutover time
Multiple Iterations of Dress Rehearsals – System Testing (60% data), UAT (90% data) and Pre- Prod (100% data)
Approach Highlights
Global Template & Pilot Implementation
Repeated for each Cluster
System Testing
UAT
Pre-Prod

## Slide 10: Holistic Testing approach with Quality gates right through design and deployment phases
Test Plan per Cluster
Test Plan per Cluster
Dedicated Test Manager for Test Management and reporting
System Testing critical scenarios of a legal entity and cover representative SBUs in Pilot
System Testing for each cluster with focus on the changed business process / solution component pertaining to a legal entity of the cluster
Customer to execute System Integration comprising testing of integration testing and User Acceptance Test
Regression Testing during each cluster rollout
Relevant Performance Testing scenarios for testing in Pilot phase
Approach Highlights
Master Test Plans
Test Activities
Test Activities
Test Activities
Monitoring, Reporting & Adjusting
Requirements
User Acceptance Test
Functional Specs and Design
Design Specification
System Build and Unit Test
System Testing
System Integration Testing
Conference Room Pilot: Design Validation
Performance Testing
Regression Testing
Smoke Testing
Other Test Activities
Re-usables from customer
Testing Toolkit
Accelerators
Test Plan per Cluster
Test Strategy

## Slide 11: Holistic Testing Approach – Pilot implementation
Phase | Testing | Objective | Who prepares | Who Executes | Who Supports
Solution Definition | Conference Room Pilot | Validate process design based on out-of-the-box product features | Capgemini | Capgemini | Customer (validates CRP scenarios)
Solution Development | Unit Testing | Test the developed objects based on user process steps that can be invoked by users | Capgemini | Capgemini | -
Solution Development | System Testing | Test the overall solution including custom objects by testing business flows executed in E - Business suite | Capgemini | Capgemini | Customer (validates SIT scenarios)
Solution Development | System Integration Testing | Test the integration of E - Business suite with other systems | Customer | Customer | Capgemini (defect fixing)
Implementation | User Acceptance Testing | Test the overall solution including custom objects by testing business flows executed in E - Business suite and integration with other systems | Customer | Customer | Capgemini (defect fixing)
Implementation | Performance Testing | Test the overall system performance based on critical processes involving interfaces, batch jobs and reports. | Customer | Customer | Capgemini (creates test scripts on EBS side, tunes performance of custom EBS components)

## Slide 12: Holistic Testing Approach – Cluster Rollout
Phase | Testing | Objective | Who prepares | Who Executes | Who Supports
Solution Development | Unit Testing | Test the objects developed in cluster based on user process steps that can be invoked by users | Capgemini | Capgemini | -
Solution Development | System Testing | Test the solution for changed custom components by testing business flows executed in E - Business suite | Capgemini | Capgemini | 
Solution Development | Regression Testing | Test the solution based on identified scenarios to ensure that there is no negative impact post pilot go-live on the solution with addition of new countries during cluster rollouts. | Capgemini | Capgemini | 
Implementation | User Acceptance Testing | Test the solution for the changed solution components by testing business flows executed in E - Business suite and integration with other systems | Customer | Customer | Capgemini (defect fixing)

## Slide 13: Post Go Live Support Approach
Infrastructure Support
Functional Support
Technical Support
LEVEL 1
LEVEL 2
LEVEL 3
User Level
 User
 Key user
Service Desk
.
Service Desk
Infra issue or request
Application issue or request
L2 Support
L3 Support
L3 Support
Contributors Editors, …
.
Custom Code fix required
Support request
.
Scope of the Post Production Support
Infrastructure L2 & L3 Team
Scope of the Warranty
Streams | Capgemini Scope (Support Window: 8 hours, 5 days a week) | Customer Scope
Service desk |  | Publish known System downtime User Creation and Rights Management Management and Reporting
Functional | Support Business Service Request including First Month end closing Analyze & solve Support Requests raised Maintain Application Setup Apply Data Fix Manage Knowledge Repository | Key Users to handle User queries before raising support request Answer “How to” questions Translate Support Request in English Liaise with Oracle Support for Product issues
Technical & Infra | Custom Code fix Custom Code Deployment assistance | Apps DBA , db Admin & Sys Admin activities Monitor batches Monitor integration Industrialization

## Slide 14: Project Organization Structure
Finance
Stream
Lead
Technology
Architect
Capgemini Executive Sponsor
Solution Architect
Delivery Executive
Project Manager
Stream Approach
Scope split into
streams to simplify
Work
Management and
have in
-
depth
focus at each
stream
Teaming with Customer resources
To leverage Customer knowledge on business
processes and setup of current R11i environment
O2C
Stream
Lead
R12 Functional Team
–
Analysis, Design & Configuration, and Training
Technical
Team
–
CEMLI Uplift, Build and Unit Test
Data
Migration
Team
–
Data extraction, transformation and loading
DM Lead
Tech
Lead
Offshore Delivery Manager
Test
Manager & Team
-
Test Management
Account
Executive
Business Lead
Project
Manager
IT Director
Customer Steering Committee
Super Users
Functional
Stream Leads
&
Development
Manager
Test Manager
IT Team
Data Migration Manager
Development Team
Mumbai
Project Office
Onsite & Offshore
PMO
PMO
Cluster
Leads
P2P
Stream
Lead
D2R
Stream
Lead
Cluster Leads
Cluster
Leads
Customer
Location
Offshore
Location
Project Office
Onshore
Apps DBA

## Slide 15: Roles and Responsibilities
Capgemini Roles | Capgemini Team Responsibilities | Customer Counterpart | Customer Team Responsibilities
Capgemini Executive Sponsor | Overall leadership accountability for the engagement for Capgemini & Provide Quality oversights | Project Governance | A Steering Committee with representatives from business, functional and technical IT on Director level.
Account Executive | Be the sole SPOC for customer regarding all account related issues |  | 
Delivery Executive | Sets the overall direction for all of the components of the project, holds overall responsibility to manage the scope change process, stakeholders, contracts |  | 
Project Manager | Overall responsibility for the project execution, quality, schedule and deliverables from Capgemini | Project Management | Jointly manage the project with Capgemini’s Project Manager to co-ordinate and facilitate sign offs
PMO | Assists the project manager in defining and implementing project standards of processes and procedures |  | 
Solution Architect | Overall responsible for the functional solution | Business Team and Process Excellence Team (including key users on a need basis) | Provide Capgemini an understanding of current business processes in their respective stream Work with Capgemini on various R12 activities
Functional Stream Leads (Finance, P2P, O2C, D2R) | Responsible for all functional aspects of their respective streams |  | 
Functional Team | Requirement Gathering, Solution design of the modules, Configurations, Testing, Func. & Tech. Specs. |  | 
Technical Architect | Ownership of the technology solution implementation across multiple work streams | IT Team, Data Migration Lead IT DBA Team, | Provide explanation about existing 11i customizations and Bespoke systems, ensure that Customer quality standards are followed, Provide DBA & infrastructure support
Technical Lead / Data Migration Lead | Owns the technical scope of all activities under their respective streams |  | 
Development Factory: Technical Team | Manage and document technical components based on gap and impact analysis, development & deployment of customizations, unit testing, defect fixing |  | 
Data Migration Factory: Technical Team | Design, Build and test Data migration routines covering extraction, transformation and loading, Dry Runs and Data migration reconciliations |  | 
Test Manager | Responsible for planning, monitoring and reporting of all test activities during the project | IT Team | Support for planning, monitoring and reporting of all test activities during the project
Testing Factory: Testing Team | Identifies & Executes test scenarios for System Test, Performance Testing and Regression Testing |  | 

## Slide 16: Our ADM Service Model is Adjusted to Client Needs, (Baseline + On-demand Services) based on Rightshore®
Rightshore®
Onsite
Client Knowledge
Cultural/local language fit
Multilevel relationship
Understand client’s business challenges
Offshore
Industrialised delivery (Factory) located in GDC
Basic understanding of clients systems & processes
IT Competence Centre
Business Departments
Help Desk
Service Management
Service Level Measurement & Reporting
Service Level Agreement Management
Service Reporting
Escalation Management
Application Management
– 2nd Level Support –
Application & Integration Management
– 3rd Level Support –
Incident Management
Bug fixing
Problem Management
Cont. improvements
On Demand Service
(Change Request & Projects)
Project Support
Data Migration & Testing
Development Enhancement
Customising
Infrastructure & 3rd Party Management
Implementation of CRs and Projects (via Rate card)
Design
Implementation (Customising, Development, Testing)
Deployment (Data Migration, Release, Training)
2nd Level incident management according to pre-defined priorities (non business critical problems)
3rd Level problem management (business critical processes); continuous improvement program/root-cause analysis
Care taking and Integration Management – ensure integration of new applications
Service Level Management & Reporting/Measurement
Escalation Management
Contract Management
Service Model Adjustments
Service reviews
BEST PRACTICE

## Slide 17: Typical Delivery Organization
Sk
Service desk
Service Desk Tool
Integrated ITIL Processes
“Domain” IT Mgmt
Client Business Functions
Project 1 Manager
Project 2 Manager
Project 3 Manager
Project 1 Delivery
Project 2 Delivery
Project 3 Delivery
“Domain” IT Mgmt
“Domain” IT Mgmt
Innovation council, COE’s
Project 1 Delivery
Project 2 Delivery
Project 3 Delivery
“Domain IT Mgmt
Capgemini Onshore & Onsite Teams
Capgemini Offshore Teams
Skills Flow
Service Delivery Executive
Skills Flow
Support & Enhancement
Service
Delivery Manager
Domain Support Lead
Domain Support & Enhancement
Service
Offshore Domain Lead
Domain Support & Enhancement
Service
Offshore Domain Lead
Support & Enhancement
Service
Delivery Manager
Domain Support Lead
Domain Support & Enhancement
Service
Offshore Domain Lead
Support & Enhancement
Service
Domain Support & Enhancement
Service
Support & Enhancement
Service
Delivery Manager
Domain Support Lead
Project Development
Testing Services
Quality Services
Cross domain Technical Pool
Business Users Community
Project Development
Incident Flow
Incident Flow
Cross Functional Services
Delivery Manager
Domain Support Lead
Offshore Domain Lead
Notes: Onsite teams aligned to Client IT and Business domains
Offshore team – part dedicated to Domains and technology pool of similar technologies who work across domains
Supported BY testing and Quality
Supported by Innovation council and COE’s

## Slide 18: Capgemini proprietary tools & accelerators to increase productivity, predictability and reduce costs
Functional Impact Matrix
Custom Spotlighter
Data Migration Toolkit
Testing Toolkit
Country Localization Kit
Global Rollout Kit

## Slide 19
Questions and Answers